## Overview
Why did USSM create the M3 Services Tailoring Guide For Transaction Processing Services Migrations?
Purpose:
The M3 Framework was originally developed to guide agencies in buying an existing system from a provider. When agencies are purchasing transaction processing services only (versus a system and FTEs to process their transactions in that new system) they can tailor out the M3 Playbook activities and outputs that are no longer relevant due to the limited scope of a transaction processing services only migration. The Tailoring Guide is provided by Unified Shared Services Management (USSM) to help reduce the workload for agencies that are purchasing transaction processing services (and not simultaneously migrating to a new system) by identifying the M3 Playbook activities and outputs that can be omitted (project dependent) based on the limited scope (services only) of the migration. Like the M3 Playbook, the Tailoring Guide is descriptive, not prescriptive. Agencies may tailor the activities and artifacts based on their implementation, and provide justification in the relevant fields.
M3 Services Tailoring Guide Field Descriptions
Fields | Fields Description:
Header | Project Identification fields (Name, Project Phase, Description).
M3 Playbook Activities | Pre-populated locked field that lists the M3 Playbook activity associated with each artifact.
M3 Playbook Output | Locked field with the artifact(s) associated with the M3 Playbook activity. Please note: Output may appear to have been produced in an earlier activity. These are not duplicates; agencies should update the previously produced artifacts based on the objectives and guidance provided in the M3 Playbook.
Tailoring | Status: Unlocked dropdown field prepopulated with either 'Recommended', 'Omit', or 'Project Dependent'. aRecommended: denotes artifacts that are relevant for a transaction processing services only migration. Agencies should create these M3 Playbook outputs. aProject Dependent: denotes artifacts that may be relevant to a transaction processing services only migration. Agencies will determine if an artifact is 'Recommended' or 'Omitted' based on the nature of their specific project, and change the status accordingly. Agencies should explain the reason for their selection (e.g. Recommended or Omit) in the 'Agency Remarks' column. aOmit: denotes artifacts that are not relevant to a transaction processing services only migration. Though agencies may choose to create these artifacts, USSM does not expect them to do so. Agencies should explain the reason for their selection in the 'Agency Remarks' column.
M3 Playbook Phase | Locked field with the M3 Playbook Phase (0-4) during which each activity and output originates.
M3 Playbook Workstream | Locked field with the applicable M3 Playbook workstream for each artifact and activity.
USSM Remarks | If necessary USSM provides guidance, context or instruction to agencies on their specific transaction processing services only migration.
Agency Remarks | Unlocked field for Agency use to document M3 tailoring status decisions.
M3 Services Tailoring Guide Instructions
How to Complete the Guide:
Step 1: | Determine the status of each artifact. Reference the M3 Playbook's Guidance for the activity/output to make this determination. In the 'Tailoring' column, select 'Omit' or 'Recommended' for each output denoted as 'Project Dependent'. If an artifact is denoted as 'Recommended' or 'Omit', that selection is expected to remain unchanged across the Tailoring Guide.
Step 2: | Enter comments in "Agency Remarks" to explain the reason for their selection (e.g. Recommended or Omit).
Step 3: | Submit the Tailoring Guide along with the Tollgate Review documentation required to demonstrate readiness and gain approval for the relevant M3 phase. Agencies should tailor their activities and artifacts as each phase occurs, as the needs of a project may change over time.
Step 4: | Create the artifact during the course of the transaction processing services only migration.

## Tailor
Header
Name: | {Enter Agency and Project Name}
M3 Phase: | {Select USSM Project Phase}
Project Description: | {Enter Project Description and Solution }
M3 Playbook Activity | M3 Output | Tailoring | M3 Phase | M3 Work Stream | USSM Remarks | Agency Remarks
Phase 0 (Assessment)
0.1 Define Vision | Vision Statement | Recommended | Phase 0 | Program Management | Although no change in Operational State may be anticipated, there are significant benefits from working with Executive Leadership to define a common vision.
0.1 Define Vision | In-scope service area(s) and function(s) | Recommended | Phase 0 | Program Management | To facilitate strong conversation with potential providers, the customer agency must have a vision of what services it is seeking to migration (I.e. Financial Management AP and AR processing).
0.1 Define Vision | Expected Benefits | Recommended | Phase 0 | Program Management | In working with the Executive Leadership to define a common vision, a key output should include have a clear goals that speak to the mission outcomes the customers hopes to achieve.
0.1 Define Vision | High Level Timelines | Recommended | Phase 0 | Program Management | To enable good estimates from potential providers and better plan for the services migration, an understanding of the high level timeline and drivers behind the timeline is essential.
0.2 Develop Major IT Business Case | Major IT Business Case | Recommended | Phase 0 | Program Management | All projects should have a business case. However, this artifact refers to OMB Exhibit 300. Because no major IT acquisition and no capital assets are being procured, the Major IT Business case (OMB Exhibit 300) is not required.
Phase 1 (Readiness)
1.1 Establish Initial Customer PMO and Processes | Program Charter | Recommended | Phase 1 | Program Management | The purpose of the project must be documented.
1.1 Establish Initial Customer PMO and Processes | HR/Staffing Plan | Project Dependent | Phase 1 | Program Management | A PMO may not need to be established and staff onboarded, depending on the size and scope of the services being migrated.
1.1 Establish Initial Customer PMO and Processes | Program Management Plan | Recommended | Phase 1 | Program Management | Mandatory for all projects as it documents multiple required project output, including the risk, schedule, procurement, cost, communications, stakeholder, and quality artifacts.
1.1 Establish Initial Customer PMO and Processes | Initial Master Schedule | Recommended | Phase 1 | Program Management | Mandatory for all projects.
1.1 Establish Initial Customer PMO and Processes | IV&V Plan | Omit | Phase 1 | Program Management | With no change in the technology environment anticipated, IV&V is not required.
1.1 Establish Initial Customer PMO and Processes | Status Reports/Dashboards | Recommended | Phase 1 | Program Management | Reports must document progress at regular intervals.
1.2 Establish Customer Governance Structure and Processes | Governance Charter | Recommended | Phase 1 | Program Management | Decision making authorities must be identified.
1.3 Establish Customer Risk Processes | Risk Management Plan | Recommended | Phase 1 | Program Management | Regardless of size and scope of services migration, risks will be encountered. A common understanding of how the risks are monitored and documented is critical.
1.3 Establish Customer Risk Processes | Risks, Actions, Issues, and Decisions (RAID) Log | Recommended | Phase 1 | Program Management | Regardless of size and scope of services migration, risks and issues will be encountered. A method to formally record these risks and issues is required for all migrations.
1.3 Establish Customer Risk Processes | M3 Risk Assessment | Recommended | Phase 1 | Program Management | A standardized risk assessment framework presents key risk criteria to help CFO Act agencies better assess and identify risk areas in Common Solutions modernization and migrations efforts.
1.4 Conduct Procurement Planning | Procurement Plan | Project Dependent | Phase 1 | Program Management | Depending on scope and size of the project, procurement needs, tools and associated timelines may need to be developed for the services migration.
1.4 Conduct Procurement Planning | QASP | Omit | Phase 1 | Program Management | SLAs take the place of QASP.
1.5. Develop Life Cycle Cost in the Business Case | Life Cycle Cost Estimate | Recommended | Phase 1 | Program Management | Cost estimates are required for all projects.
1.6 Define Benefits of the Program | Baseline Performance and Success Metrics | Recommended | Phase 1 | Program Management | Current performance metrics must be documented.
1.6 Define Benefits of the Program | Target Performance and Success Metrics | Recommended | Phase 1 | Program Management | Target performance and success metrics are required.
1.7 Define Change Management Approach | Stakeholder Analysis | Recommended | Phase 1 | Workforce Organization & Stakeholders | All stakeholders must be identified prior to all migrations, including services only.
1.7 Define Change Management Approach | Communications Plan | Recommended | Phase 1 | Workforce Organization & Stakeholders | Regardless of size and scope of the services migration, the effect on the agency must be communicated to impacted stakeholders.
1.7 Define Change Management Approach | Migration and O&M training needs | Omit | Phase 1 | Workforce Organization & Stakeholders | No changes to the system are anticipated, so no user training is required.
1.8 Understand As-Is Workforce | As-Is Workforce Documentation | Recommended | Phase 1 | Workforce Organization & Stakeholders | Regardless of size and scope of the services migration, the current workforce must be documented.
1.8 Understand As-Is Workforce | Change Readiness Assessment | Recommended | Phase 1 | Workforce Organization & Stakeholders | Regardless of size and scope of the migration, the agency's fitness for change must be determined.
1.9 Define As-Is and Initial Target State Systems Environment | As-Is Systems Environment | Omit | Phase 1 | Technology | N/A for Services Only Migrations.
1.9 Define As-Is and Initial Target State Systems Environment | Target State Systems Environment | Omit | Phase 1 | Technology | N/A for Services Only Migrations.
1.10 Plan and Conduct Initial Data Quality Assessment | Data Governance Model | Omit | Phase 1 | Technology | N/A for Services Only Migrations.
1.10 Plan and Conduct Initial Data Quality Assessment | Data Cleansing Plan | Project Dependent | Phase 1 | Technology | Dependent on the quality of the data and the availability of customer resources.
1.11 Develop Initial Target State Concept of Operations and Scope of Services | Target State Concept of Operations | Recommended | Phase 1 | Process & Service Delivery | A Concept of Operations defines how the business will work (process, governance, etc.) in the future state.
1.11 Develop Initial Target State Concept of Operations and Scope of Services | Scope of Services updated in the Business Needs Workbook | Recommended | Phase 1 | Process & Service Delivery | Developing a Concept of Operations and Scope of Services defines how the business will work (process, governance,etc.) in the future state.
1.12 Review Standard Business Capabilities & Document Initial Business Capabilities | Requirements Management Plan | Project Dependent | Phase 1 | Process & Service Delivery | Required if the services being migrated require integration with unique business requirements.
1.12 Review Standard Business Capabilities & Document Initial Business Capabilities | Business Needs Workbook | Recommended | Phase 1 | Process & Service Delivery | Business Needs Workbook is used to map business capabilities with FIBF LoB standardized services list. It is to be tailored for Services Only migrations.
1.12 Review Standard Business Capabilities & Document Initial Business Capabilities | Business Capabilities | Recommended | Phase 1 | Process & Service Delivery | Business capabilities/service functions to be migrated must be documented.
Phase 2 (Selection)
2.1 Select Provider for Engagement | Business Needs Workbook | Recommended | Phase 2 | Program Management | Business Needs Workbook is used to map business capabilities with FIBF LoB standardized services list. It is to be tailored for Services Only migrations.
2.1 Select Provider for Engagement | Evaluation Criteria | Recommended | Phase 2 | Program Management | Customer will develop criteria to evaluate providers.
2.1 Select Provider for Engagement | Draft RFI and Responses (Commercial Only) | Project Dependent | Phase 2 | Program Management | Dependent on whether a commercial or federal provider is being considered.
2.1 Select Provider for Engagement | Implementation Approach/Schedule | Recommended | Phase 2 | Program Management | Approach and schedule are required.
2.1 Select Provider for Engagement | Price Estimates for Engagement, Migration, and Operations and Maintenance (O&M) | Recommended | Phase 2 | Program Management | Cost estimates are required.
2.1 Select Provider for Engagement | Provider Assessment Report (Federal Only) | Project Dependent | Phase 2 | Program Management | Dependent on whether a commercial or federal provider is being considered.
2.1 Select Provider for Engagement | Engagement Phase Interagency Agreement (IAA) (Federal Only) | Project Dependent | Phase 2 | Program Management | Dependent on whether a commercial or federal provider is chosen. Agencies may do a single IAA for engagement and implementation.
2.1 Select Provider for Engagement | Draft RFP (Commercial Only) | Project Dependent | Phase 2 | Program Management | Dependent on whether a commercial or federal provider is chosen.
2.2 Update Life Cycle Cost Estimate (LCCE) for Engagement, Migration, and O&M | LCCE for Engagement, Migration, and O&M | Recommended | Phase 2 | Program Management | Cost estimates are required.
2.3 Monitor and Control Program Execution | Procurement Plan | Project Dependent | Phase 2 | Program Management | Depending on scope and size of the project, procurement needs, tools and associated timelines may need to be developed for the services migration.
2.3 Monitor and Control Program Execution | Initial Master Schedule | Recommended | Phase 2 | Program Management | Mandatory for all projects.
2.3 Monitor and Control Program Execution | HR/Staffing Plan | Project Dependent | Phase 2 | Program Management | A PMO may not need to be established, with roles and responsibilities defined and staff onboarded, depending on the size and scope of the services being migrated.
2.3 Monitor and Control Program Execution | Program Management Plan | Recommended | Phase 2 | Program Management | Mandatory for all projects as it documents multiple required project output, including the risk, schedule, procurement, cost, communications, stakeholder, and quality artifacts.
2.3 Monitor and Control Program Execution | IV&V Plan | Omit | Phase 2 | Program Management | With no change in the technology environment anticipated, IV&V is not required.
2.3 Monitor and Control Program Execution | Status Reports/Dashboards | Recommended | Phase 2 | Program Management | Reports must document progress at regular intervals.
2.4 Maintain and Execute Risk Processes | Risk Management Plan | Recommended | Phase 2 | Program Management | Regardless of size and scope of services migration, risks will be encountered. A common understanding of how the Risks are monitored and documented is critical.
2.4 Maintain and Execute Risk Processes | RAID Log | Recommended | Phase 2 | Program Management | Regardless of size and scope of services migration, risks and issues will be encountered. A method to formally record these risks and issues is required for all migrations.
2.4 Maintain and Execute Risk Processes | M3 Risk Assessment | Recommended | Phase 2 | Program Management | A standardized risk assessment framework presents key risk criteria to help CFO Act agencies better assess and identify risk areas in Common Solutions modernization and migrations efforts.
2.5 Design Labor Relations Outreach | Labor Relations Strategy | Project Dependent | Phase 2 | Workforce Organizations and Stakeholders | Assessment of impact on workforce and Collective Bargaining Agreements (CBAs) - if any - is required.
2.6 Develop Change Management Plan | Change Management Plan | Recommended | Phase 2 | Workforce Organizations and Stakeholders | Regardless of size and scope of the migration, planning must account for impact to the agency.
2.6 Develop Change Management Plan | Communications Plan | Recommended | Phase 2 | Workforce Organizations and Stakeholders | Regardless of size and scope of the services migration, the effect on the agency must be communicated to impacted stakeholders.
2.6 Develop Change Management Plan | Baseline Readiness Assessment | Recommended | Phase 2 | Workforce Organizations and Stakeholders | Regardless of size and scope of the migration, the stakeholders' receptiveness to change must be determined.
2.7 Conduct Initial Data Cleansing Activities | Data Cleansing Plan | Project Dependent | Phase 2 | Technology | Customers who will not perform data cleansing should inform their provider of data quality issues.
2.7 Conduct Initial Data Cleansing Activities | Data Cleansing Scripts | Project Dependent | Phase 2 | Technology | Customers who will not perform data cleansing should inform their provider of data quality issues.
2.8 Develop a Decommission Plan | Decommission Plan | Recommended | Phase 2 | Technology | N/A Services only-
2.9 Understand As-Is Business Processes | Business Process Reengineering Strategy | Project Dependent | Phase 2 | Process & Service Delivery | If business processes are changing due to the services being performed by an outside organization, an updated BPR strategy may be needed.
2.9 Understand As-Is Business Processes | Validated As-Is Process Maps | Recommended | Phase 2 | Process & Service Delivery | For easy transition of internal processes to an external organization, a strong understanding of the As-Is process is required.
Phase 3 (Engagement)
3.1 Integrate PMO Structures | Program Charter | Recommended | Phase 3 | Program Management | The purpose of the project must be agreed by Customer and Provider.
3.1 Integrate PMO Structures | HR/Staffing Plan | Recommended | Phase 3 | Program Management | Provider must document strategy for onboarding the team that will be performing the migration.
3.1 Integrate PMO Structures | IMS | Recommended | Phase 3 | Program Management | Mandatory for all projects.
3.1 Integrate PMO Structures | Program Management Plan | Recommended | Phase 3 | Program Management | Mandatory for all projects as it documents multiple required project output, including the risk, schedule, procurement, cost, communications, stakeholder, and quality artifacts.
3.1 Integrate PMO Structures | IV&V Plan | Omit | Phase 3 | Program Management | With no change in the technology environment anticipated, IV&V is not required.
3.2 Integrated Governance Structures | Governance Charter | Recommended | Phase 3 | Program Management | Decision making authorities and communication channels must be identified and integrated.
3.3 Update and Maintain Procurement Plans | Procurement Plan | Project Dependent | Phase 3 | Program Management | Depending on scope and size of the project, procurement needs, tools and associated timelines may need to be developed for the services migration.
3.4 Monitor and Control Program Execution | Program Management Plan | Recommended | Phase 3 | Program Management | Mandatory for all projects as it documents multiple required project output, including the risk, schedule, procurement, cost, communications, stakeholder, and quality artifacts.
3.4 Monitor and Control Program Execution | Status Reports/Dashboards | Recommended | Phase 3 | Program Management | Reports must document progress at regular intervals.
3.4 Monitor and Control Program Execution | IV&V Plan | Omit | Phase 3 | Program Management | With no change in the technology environment anticipated, IV&V is not required.
3.4 Monitor and Control Program Execution | Change Request Log | Project Dependent | Phase 3 | Program Management | May be required if changes are made to the initial scope of services being migrated.
3.4 Monitor and Control Program Execution | Change Request Form | Project Dependent | Phase 3 | Program Management | May be required if changes are made to the initial scope of services being migrated.
3.4 Monitor and Control Program Execution | IMS | Recommended | Phase 3 | Program Management | Mandatory for all projects.
3.4 Monitor and Control Program Execution | Lessons Learned Report | Recommended | Phase 3 | Program Management | Required for all migrations.
3.5 Maintain and Execute Risk Processes | Risk Management Plan | Recommended | Phase 3 | Program Management | Regardless of size and scope of services migration, risks will be encountered. A common understanding of how the risks are monitored and documented is critical.
3.5 Maintain and Execute Risk Processes | RAID Log | Recommended | Phase 3 | Program Management | Regardless of size and scope of services migration, risks and issues will be encountered. A method to formally record these risks and issues is required for all migrations.
3.5 Maintain and Execute Risk Processes | M3 Risk Assessment | Recommended | Phase 3 | Program Management | A standardized risk assessment framework presents key risk criteria to help CFO Act agencies better assess and identify risk areas in Common Solutions modernization and migrations efforts.
3.6 Finalize Migration Approach | Migration Phase IAA Terms and Conditions (Federal Only) | Project Dependent | Phase 3 | Program Management | Dependent on whether a commercial or federal provider is chosen.
3.6 Finalize Migration Approach | Intent to Exercise Migration Option (Commercial) | Project Dependent | Phase 3 | Program Management | Dependent on whether a commercial or federal provider is chosen.
3.6 Finalize Migration Approach | Migration Approach, including Technical Strategies | Project Dependent | Phase 3 | Program Management | Technical strategies will not be applicable. However, depending on the size and scope of the migration, a phased implementation may be necessary, requiring a release strategy.
3.6 Finalize Migration Approach | Go/No-Go Criteria for Go-Live Assessment | Recommended | Phase 3 | Program Management | Required for all migrations.
3.6 Finalize Migration Approach | IMS | Recommended | Phase 3 | Program Management | Mandatory for all projects.
3.6 Finalize Migration Approach | Decommission Plan | Omit | Phase 3 | Program Management | N/A Services only-
3.7 Update LCCE for Migration and O&M | LCCE for Migration and O&M | Recommended | Phase 3 | Program Management | Mandatory for all projects.
3.8 Engage with Labor Relations | Labor Relations Strategy | Project Dependent | Phase 3 | Workforce Organization and Stakeholders | Assessment of impact on workforce and Collective Bargaining Agreements (CBAs) - if any - is required.
3.9 Execute Change Management Plan | Change Management Plan | Project Dependent | Phase 3 | Workforce Organization and Stakeholders | Regardless of size and scope of the migration, impact to the agency must be accounted.
3.9 Execute Change Management Plan | Communications Plan | Recommended | Phase 3 | Workforce Organization and Stakeholders | Regardless of size and scope of the services migration, the effect on the agency must be communicated to impacted stakeholders.
3.9 Execute Change Management Plan | Readiness Assessment | Recommended | Phase 3 | Workforce Organization and Stakeholders | Regardless of size and scope of the migration, the ability of stakeholders to adapt to change must be determined.
3.9 Execute Change Management Plan | Workforce Assessment | Recommended | Phase 3 | Workforce Organization and Stakeholders | Regardless of size and scope of the services migration, the impact of the change on the workforce must be determined.
3.10 Develop Training Plan | Training Plan | Project Dependent | Phase 3 | Workforce Organization and Stakeholders | If process changes are expected, training needs and plan should be assessed/developed to train on the change.
3.11 FInalize Requirements | Requirements Management Plan | Recommended | Phase 3 | Technology | Required if the services being migrated require integration with unique business requirements.
3.11 Finalize Requirements | Requirements Traceability Matrix (RTM) | Project Dependent | Phase 3 | Technology | Required if the services being migrated require integration with unique business requirements.
3.12 Conduct Requirements Fit-GAP Analysis | Gap Analysis Report | Project Dependent | Phase 3 | Technology | May be required if there are gaps between the as-is capabilities and target state capabilities.
3.12 Conduct Requirements Fit-Gap Analysis | RTM | Project Dependent | Phase 3 | Technology | May be required if the services being migrated require integration with or changes to customer systems that do not already exist.
3.13 Finalize Target State Systems Environment | Validated and Updated As-Is Systems Environment | Omit | Phase 3 | Technology | N/A Services only-
3.13 Finalize Target State Systems Environment | Target State Systems Environment | Project Dependent | Phase 3 | Technology | May be required if standardization of services and activities need to occur before or during the purchase of the service.
3.14 Develop Technical Strategy | Test Plan | Project Dependent | Phase 3 | Technology | N/A Services only-
3.14 Develop Technical Strategy | Configuration Management Plan | Project Dependent | Phase 3 | Technology | Technical strategies may need to be developed to govern the need for connectivity between the service provider and the customer's existing environment and all relevant sites, including disaster recovery sites.
3.14 Develop Technical Strategy | CooP and Disaster Recovery Plan | Project Dependent | Phase 3 | Technology | Technical strategies may need to be developed to govern the need for connectivity between the service provider and the customer's existing environment and all relevant sites, including disaster recovery sites.
3.14 Develop Technical Strategy | Interface Strategy | Project Dependent | Phase 3 | Technology | Technical strategies may need to be developed to govern the need for connectivity between the service provider and the customer's existing environment and all relevant sites, including disaster recovery sites.
3.14 Develop Technical Strategy | Enhancement Strategy | Project Dependent | Phase 3 | Technology | Technical strategies may need to be developed to govern the need for connectivity between the service provider and the customer's existing environment and all relevant sites, including disaster recovery sites.
3.14 Develop Technical Strategy | Decommission Plan | Omit | Phase 3 | Technology | N/A Services only-
3.15 Prepare Data for Mock Conversions (Data Cleansing, Data Mapping) | Data Cleansing Plan | Omit | Phase 3 | Technology | Customers who will not perform data cleansing should inform their provider of data quality issues.
3.15 Prepare Data for Mock Conversions (Data Cleansing, Data Mapping) | Data Cleansing Scripts | Project Dependent | Phase 3 | Technology | Customers who will not perform data cleansing should inform their provider of data quality issues.
3.15 Prepare Data for Mock Conversions (Data Cleansing, Data Mapping) | Documented Data Structure and Mapping | Project Dependent | Phase 3 | Technology | Customers who will not perform data cleansing should inform their provider of data quality issues.
3.15 Prepare Data for Mock Conversions (Data Cleansing, Data Mapping) | Data Conversion Plan | Project Dependent | Phase 3 | Technology | Customers who will not perform data cleansing should inform their provider of data quality issues.
3.16 Finalize Target State Concept of Operations | Target State Concept of Operations | Recommended | Phase 3 | Process & Service Delivery | A Concept of Operations defines how the business will work (process, governance, etc.) in the future state.
3.17 Define Contact Center Structure | Contact Center Strategy | Omit | Phase 3 | Process & Service Delivery | N/A Services only-
3.18 Define Service Level Agreements | Operations & Maintenance (O&M) Service Level Agreements (SLAs) | Recommended | Phase 3 | Process & Service Delivery | Required to document and measure Provider performance once migration is complete.
Phase 4 (Migration)
4.1 Monitor and Control Program Execution | Change Request Form | Recommended | Phase 4 | Program Management | May be required if changes are made to the initial scope of services being migrated.
4.1 Monitor and Control Program Execution | Change Request Log | Recommended | Phase 4 | Program Management | May be required if changes are made to the initial scope of services being migrated.
4.1 Monitor and Control Program Execution | IMS | Project Dependent | Phase 4 | Program Management | Mandatory for all projects.
4.1 Monitor and Control Program Execution | Program Management Plan | Recommended | Phase 4 | Program Management | Mandatory for all projects as it documents multiple required project output, including the risk, schedule, procurement, cost, communications, stakeholder, and quality artifacts.
4.1 Monitor and Control Program Execution | IV&V Plan | Omit | Phase 4 | Program Management | With no change in the technology environment anticipated, IV&V is not required.
4.2 Maintain and Execute Risk Processes | Risk Management Plan | Recommended | Phase 4 | Program Management | Regardless of size and scope of services migration, risks will be encountered. A common understanding of how the risks are monitored and documented is critical.
4.2 Maintain and Execute Risk Processes | RAID Log | Recommended | Phase 4 | Program Management | Regardless of size and scope of services migration, risks and issues will be encountered. A method to formally record these risks and issues is required for all migrations.
4.2 Maintain and Execute Risk Processes | M3 Risk Assessment | Recommended | Phase 4 | Program Management | A standardized risk assessment framework presents key risk criteria to help CFO Act agencies better assess and identify risk areas in Common Solutions modernization and migrations efforts.
4.3 Develop O&M Governance Process | O&M Governance Charter | Omit | Phase 4 | Program Management | Replaced by SLA.
4.3 Develop O&M Governance Process | RAID Log | Recommended | Phase 4 | Program Management | Regardless of size and scope of services migration, risks and issues will be encountered. A method to formally record these risks and issues is required for all migrations.
4.4 Prepare O&M Scope of Services and Contracts | O&M Contract or IAA | Recommended | Phase 4 | Program Management | Required.
4.5 Assess Readiness for Go-Live | Contingency Plan | Omit | Phase 4 | Program Management | Technology related contingencies would remain unchanged in a services only migration. Other performance measures are accounted for in the SLAs.
4.5 Assess Readiness for Go-Live | Go/No-Go Readiness Criteria | Recommended | Phase 4 | Program Management | Regardless of size and scope of the migration, the success criteria for the stakeholders' acceptance of the change must be pre-determined.
4.5 Assess Readiness for Go-Live | Go/No-Go Assessment Report | Recommended | Phase 4 | Program Management | Regardless of size and scope of the migration, a formal report of the decisions leading to Go/No-Go is required.
4.6 Life Cycle Cost Estimate (LCCE) for O&M | LCCE for O&M | Recommended | Phase 4 | Program Management | Mandatory for all projects.
4.7 Design Target State Organization | Target State Organization Design | Recommended | Phase 4 | Workforce Organization and Stakeholders | Regardless of size and scope of the services migration, any change to the workforce must be documented.
4.7 Design Target State Organization | Workforce Assessment | Recommended | Phase 4 | Workforce Organization and Stakeholders | Regardless of size and scope of the services migration, the impact of the change on the workforce must be documented.
4.7 Design Target State Organization | Workforce Transition Strategy | Recommended | Phase 4 | Workforce Organization and Stakeholders | A strategy is needed to transition/reassign resources displaced by the migration of services.
4.8 Execute Workforce Transition and Prepare for Go-Live | Communications Plan | Recommended | Phase 4 | Workforce Organization and Stakeholders | Regardless of size and scope of the services migration, the effect on the agency must be communicated to impacted stakeholders.
4.8 Execute Workforce Transition and Prepare for Go-Live | Targeted Cutover Communications Plan | Recommended | Phase 4 | Workforce Organization and Stakeholders | Regardless of size and scope of the services migration, the effect on the agency must be communicated to impacted stakeholders.
4.8 Execute Workforce Transition and Prepare for Go-Live | Workforce Assessment | Recommended | Phase 4 | Workforce Organization and Stakeholders | Regardless of size and scope of the services migration, the impact of the change on the workforce must be documented.
4.8 Execute Workforce Transition and Prepare for Go-Live | Readiness Assessment | Recommended | Phase 4 | Workforce Organization and Stakeholders | Regardless of size and scope of the migration, the stakeholders' adaptability to the change must be assessed against the criteria.
4.8 Execute Workforce Transition and Prepare for Go-Live | Change Management Plan | Recommended | Phase 4 | Workforce Organization and Stakeholders | Regardless of size and scope of the migration, impact to the agency must be accounted.
4.9 Execute Training for Go-Live | Training Plan | Omit | Phase 4 | Workforce Organization and Stakeholders | No changes to the system are anticipated, so no user training is required.
4.9 Execute Training for Go-Live | Training Materials | Omit | Phase 4 | Workforce Organization and Stakeholders | No changes to the system are anticipated, so no user training is required.
4.9 Execute Training for Go-Live | Training Evaluations | Omit | Phase 4 | Workforce Organization and Stakeholders | No changes to the system are anticipated, so no user training is required.
4.10 Execute Labor Relations Strategy | Labor Relations Strategy | Project Dependent | Phase 4 | Workforce Organization and Stakeholders | Assessment of impact on workforce and Collective Bargaining Agreements (CBAs) - if any - is required.
4.11 Conduct Security and Privacy Reviews | Security Documentation, including Security Test Results and ATO | Omit | Phase 4 | Technology | N/A for Services Only Migrations.
4.11 Conduct Security and Privacy Reviews | Privacy Documentation, including Initial Privacy Assessment, FIPS 199, System of Records Notice (SORN), Privacy Impact Assessment | Omit | Phase 4 | Technology | N/A for Services Only Migrations.
4.12 Define Roles and User Access | Baselined List of ID Credentials | Recommended | Phase 4 | Technology | Needed for provider to access customer systems, understand customer segregation of duties processes, and prevent Governance Risk and Compliance (GRC) violations. Provider may also need additional security clearance.
4.13 Configure Systems | RTM | Project Dependent | Phase 4 | Technology | May be required if the services being migrated require integration with or changes customer systems that do not already exist.
4.13 Configure Systems | Configuration Workbooks | Omit | Phase 4 | Technology | N/A for Services Only Migrations.
4.14 Design and Develop Interfaces | Interface Control Document | Omit | Phase 4 | Technology | N/A for Services Only Migrations.
4.15 Design and Develop Reports | Reports Design Document | Omit | Phase 4 | Technology | N/A for Services Only Migrations.
4.16 Conduct Mock Conversion | Data Conversion Plan | Project Dependent | Phase 4 | Technology | Customers who will not perform data cleansing should inform their provider of data quality issues.
4.16 Conduct Mock Conversion | Mock Conversion Report | Project Dependent | Phase 4 | Technology | Customers who will not perform data cleansing should inform their provider of data quality issues.
4.16 Conduct Mock Conversion | Conversion Defect Log | Project Dependent | Phase 4 | Technology | Customers who will not perform data cleansing should inform their provider of data quality issues.
4.17 Test Systems and Processes | Test Plan | Omit | Phase 4 | Technology | N/A for Services Only Migrations.
4.17 Test Systems and Processes | Test Scripts | Omit | Phase 4 | Technology | N/A for Services Only Migrations.
4.17 Test Systems and Processes | Test Results Report | Omit | Phase 4 | Technology | N/A for Services Only Migrations.
4.17 Test Systems and Processes | Test Defect Log | Omit | Phase 4 | Technology | N/A for Services Only Migrations.
4.17 Test Systems and Processes | RTM | Project Dependent | Phase 4 | Technology | May be required if the services being migrated require integration with or changes customer systems that do not already exist.
4.18 Develop and Execute Cutover Plan for Go-Live | Cutover Plan | Omit | Phase 4 | Technology | N/A for Services Only Migrations.
4.18 Develop and Execute Cutover Plan for Go-Live | Decommission Plan | Omit | Phase 4 | Technology | N/A Services only-
4.19 Finalize Service level Agreements | O&M SLA | Recommended | Phase 4 | Process & Service Delivery | Required to document and measure Provider performance once migration is complete.
4.20 Design Target State Processes | Target State Process Maps | Recommended | Phase 4 | Process & Service Delivery | If business processes are changing due to the services being performed by an outside organization, process maps are needed.
4.20 Design Target State Processes | Standard Operating Procedures (SOPs) | Recommended | Phase 4 | Process & Service Delivery | SOPs are needed because business processes are changing due to the services being performed by an outside organization.
4.20 Design Target State Processes | Business Process Reengineering Strategy | Project Dependent | Phase 4 | Process & Service Delivery | If business processes are changing due to the services being performed by an outside organization, an updated BPR strategy may be needed.
Phase 5 (Operations)
5.1 Review Performance Against Expected Benefits | Final Report on Success Metrics | Recommended | Phase 5 | Program Management | Final performance metrics must be documented.
5.2 Collect Lessons Learned | Lessons Learned Questionnaire | Recommended | Phase 5 | Program Management | Required for all migrations.
5.2 Collect Lessons Learned | Lessons Learned Report | Recommended | Phase 5 | Program Management | Required for all migrations.
5.3 Implement O&M Governance | O&M Governance Charter | Recommended | Phase 5 | Program Management | Required for all migrations.
5.3 Implement O&M Governance | O&M SLA Performance Reports | Recommended | Phase 5 | Program Management | Required to document and measure Provider performance once migration is complete.
5.3 Implement O&M Governance | Change Request Log | Recommended | Phase 5 | Program Management | May be required if changes are made to the initial scope of services being migrated.
5.4 Support Stabilization and Perform Change Management | Completed Training Evaluations | Project Dependent | Phase 5 | Workforce Organization and Stakeholders | If customer agency has staff remaining that are affected by the services migration, training for their new role is required and therefore so are training evaluations.
5.4 Support Stabilization and Perform Change Management | O&M Communications and Training Plan | Recommended | Phase 5 | Workforce Organization and Stakeholders | Regardless of size and scope of the services migration, the effect on the agency must be communicated to impacted stakeholders.
5.4 Support Stabilization and Perform Change Management | Communications Materials | Recommended | Phase 5 | Workforce Organization and Stakeholders | Regardless of size and scope of the services migration, the effect on the agency must be communicated to impacted stakeholders.
5.4 Support Stabilization and Perform Change Management | Training Materials | Project Dependent | Phase 5 | Workforce Organization and Stakeholders | If customer agency has staff remaining that are affected by the services migration, training for their new role is required.
5.5 Maintain Applications Post Go-Live | Post Implementation and Evaluation Report | Omit | Phase 5 | Technology | N/A Services only-
5.6 Decommission Legacy Systems | Decommission Report | Omit | Phase 5 | Technology | N/A Services only-
5.7 Conduct Continuous Process Improvement | Process Flows | Recommended | Phase 5 | Process & Service Delivery | Use final performance metrics to monitor operations and identify improvement opportunities.
5.7 Conduct Continuous Process Improvement | SOPs | Recommended | Phase 5 | Process & Service Delivery | SOPs are needed because business processes are changing due to the services being performed by an outside organization.
5.9 Monitor and Update SLAs (also referenced in 5.7 and 5.8) | O&M SLAs | Recommended | Phase 5 | Process & Service Delivery | Required to document and measure Provider performance once migration is complete.
Other Agency Items Tailored In
Recommended
Project Dependent
Omit